## Sheet1
North East and North Cumbria (NENC) Integrated Care System (ICS) Healthier and Fairer Programme
Poverty Proofing© Workplan |  | 2023/ 2024 |  |  |  | 2024/ 2025 |  |  |  | 2025/ 2026 |  |  |  | 2026/ 2027 |  |  |  | 2027/ 2028 |  |  |  | Governance Group | Core Objective
Item | Deliverable description | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Steering | 1-5
1 | Further develop the Poverty Proofing© approach to involving local people, communities and health champions. |  |  | ü | [17 empty] | Co Prod | 1
2 | Create a NENC Poverty Proofing© team and approach that supports making the Poverty Proofing© plan happen. | ü | [19 empty] | Steering Group | 1-5
3 | Make a NENC Poverty Proofing© work plan and make sure this is shared and discussed in as many places as possible. Keep talking about the plan and make changes to it if we need to. | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Steering Group | 1-5
4 | Make a NENC Poverty Proofing© Community of practice so people who are interested in Poverty Proofing© can get together either in person or using technology to share ideas and support each other. | [20 empty] | Steering Group | 5
5 | Find out what is already happening about Poverty Proofing© across the NENC ICS. | ü | [19 empty] | Steering Group | 1-5
6 | Make a number of patient pathways 'poverty proofed' and use these as examples. |  |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Steering Group | 3
7 | Develop and make sure organisations sign up to making what they do 'poverty proofed.' |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Pathways | 3
8 | Develop and use a NENC Poverty Proofing© toolkit to help organisations be poverty proofed. |  |  |  | ü | [16 empty] | Culture Change | 2
9 | Explore the development of a NENC Poverty Proofing© standard so people know that services have been developed to make sure they take into account poverty and its impact. |  |  | ü | ü | [16 empty] | Culture Change | 2
10 | Develop a training offer for Poverty Proofing© so people and the places they work for can be trained in how to be poverty proofed. |  |  | ü | ü | [16 empty] | Culture Change | 2
11 | Commission an evaluation of the workstream. | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Programme of Health Literacy | 4
12 |  |  |  | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | ü | Evaluation | 5